## Strategic Mission
Our Stakeholders
Mission
To be the top electronics manufacturing services provider in the market—trusted to become better each passing day—by leveraging our uniqueness, evolving persistently, maintaining stability and efficiency, and delivering electronics manufacturing excellence.
Vision
We create enduring value for all our stakeholders by optimizing customer appreciation, human fulfillment, financial robustness, and supplier and community engagement.
Each individual advances our mission and develops themselves along with the company.

## Parties
COTO Log: Interested Parties List Rev. A
Interested Party | Int / Ext | Reason for Inclusion (Factors)
Top Management | Internal | Has direct responsibility for management of ACI, including sales growth and long term financial health
Ownership / BoD / Family | Internal | Concerned with returns, equity, governance, and transition management
Employees / Staff (General) | Internal | Directly responsible for manufacture of products, delivery of service
Administration | Internal | Provides administrative, human resource, and non-manufacturing support
IT | Internal | Provides Information Technology and data management services
Financial Entities | External | Provides funding, transactions, credit, insurance and other financial assistance
Customers (current or potential) | External | Purchase or could purchase our products and services
End Customer / Product End User | External | End user of our products and services
Suppliers | External | Provides our raw materials and critical support services
Competitors | External | Concerned with ACIs market share, stability, partnerships, maneuvers and industry impact
Legal | External | Provides legal services
Government & Regulatory Bodies | External | Mandates regulatory requirements, including ITAR / EAR / prohibited country transactions
Certification Body | External | Audit for ISO 9001 compliance, issue certifications
Industry Associations | External | Provides recognized guidelines for measurement and manufacturing, networking opps
Local Community | External | Impacted by our activities in the region
*Management is an interested party as whole that we seprated into select subcomponents/departments for ease of internal clarity and grouping. Some depts may not be explicity listed as interested parties as they are captured within other internal/external parties (e.g. ops).

## Issues
|  | COTO Log: Issues List | Rev. A
Unique ID | Interested Party | Issue of Concern (Needs, Expectations, Deliverables) | Bias | Processes/Depts Affected | Within Scope of QMS? | Treatment Method | Record Reference / Notes
1 | Top Management / Quality | QMS processes must be efficient and effective | Mixed | All Processes/Depts | Yes | Risk Register / Opp Register | See Risk Register / Opp Register
2 | Top Management / Quality | Company must maintain Organizational Knowledge | Risk | All Processes/Depts | Yes | Risk Register | See Risk Register
3 | Top Management / Ownership / Financial Entities | Company must remain financially healthy | Risk | All Processes/Depts | No | Manage company finances appropriately; utilize CPA/CFO services as needed | Financials (confidential)
4 | Ownership / BoD / Family | Concerned with returns, equity, governance, and transition management | Mixed | Executive | No | Board Meetings, legal services, outside experts | Books (confidential)
5 | Top Management | Loss of our core differentiators and uniqueness | Risk | All Processes/Depts | Yes | Risk Register | See Risk Register
6 | Top Management | Too much change, too quickly | Risk | All Processes/Depts | Yes | Risk Register | See Risk Register
7 | Top Management | Keep current with industry advances (tech/methods) | Mixed | All Processes/Depts | No | Low risk, proceed normally for now | Done as normal part of business
8 | Administration | Company must maintain sufficient and capable staff | Risk | All Processes/Depts | Yes | Risk Register | See Risk Register, hiring records (confidential)
9 | Administration | Provides all corporate support activities | Risk | Admin | No | No Action: largely satisfied for now | Very low risk / Standard office protocol / No special actions required
10 | Employee / Staff | Require appropriate training and development | Mixed | All Processes/Depts | Yes | See Risk Register / Training provided / Opp Register | See Risk Register / Opp Register, training records, audit records, etc.
11 | Employee / Staff | Expect to be compensated | Risk | HR/Training | No | Use company profitability increases to reward employees by individual performance and contribution to our long-term progress and mission/vision | Financials/Payroll (confidential)
12 | Employee / Staff | Require correct information and tools to do their job | Risk | All Processes | Yes | Risk Register / FMEAs | See Risk Register / Correct documents and tooling provided
13 | IT | Must create a comprehensive and effective system of IT/telecom resources and services | Risk | IT | Yes | Risk Register | See Risk Register; Audits
14 | IT | Provides redundancy and backup plans | Risk | IT | Yes | Risk Register | See Risk Register; Audits
15 | IT | Services the IT systems and equipment | Risk | IT | No | Tech vendor for backup to ACI tech staff including emergencies, projects, maintenance and advice. | Low risk; no history of systemic hardware/software failure outside tech company utilized for emergency situations
16 | Customers / Employees | Requires adequate equipment and facilities; safe working conditions | Risk | All Processes/Depts | Yes | Risk Register / FMEA | See Risk Register
17 | Customers (current or potential) | Expect high quality products | Risk | Production | Yes | Risk Register / FMEAs | See Risk Register
18 | Customers (current or potential) | Expect on time delivery | Risk | Packing/Shipping | Yes | Risk Register / FMEAs | See Risk Register
19 | Customers (current or potential) | Concerned about price | Risk | Sales/PM/Marketing | No | Good control of finances, productivity, reporting, and quotation methods and follow through. Management will always try to meet customer's price expectations; largely satisfied for now | Standard office protocol / No special actions required
20 | Customers (current or potential) | Expect good customer service | Risk | Sales/PM/Marketing | Yes | Risk Register | See Risk Register
21 | Customers (current or potential) | Flows down their QMS requirements | Risk | Engineering | Yes | Risk Register / Engineering Services FMEA; Sales order review | Risk Register; Order acceptance records
22 | Customers (potential) | Targeted for company growth | Opportunity | All Processes/Depts | No | Opportunity Register | Opportunity Register / Financials (confidential)
23 | Customers (current) | If happy, current customers could expand current business | Opportunity | Sales/PM/Marketing | No | Opportunity Register | See Opportunity Register
24 | Customers (current or potential) | Consolidation of assembly operations | Opportunity | All Processes/Depts | Yes | Opportunity Register | Opportunity Register
25 | Customers (current or potential) | Better functional SMT operations which is central to growth | Opportunity | Engineering | Yes | Opportunity Register | See Opportunity Register
26 | Customers (current or potential) | More efficient labor utilization and feedback into our quote system | Opportunity | Production | Yes | Opportunity Register | See Opportunity Register
27 | Customers (current or potential) | New inventory system to transition from kits to centralized inventory will enhance controls, boost customer confidence, improve purchasing, and save space. | Opportunity | Receiving/Inventory | Yes | Opportunity Register | See Opportunity Register
28 | Customers / Suppliers / Stakeholders | Could be source of referrals to new customers | Opportunity | Sales/PM/Marketing | No | Opportunity Register | See Opportunity Register
29 | End Customer / Product End User | Expect high quality products | Risk | Production | Yes | See entry for Direct Customer above | See entry for Direct Customer above
30 | End Customer / Product End User | Expect on time delivery | Risk | Packing/Shipping | Yes | See entry for Direct Customer above | See entry for Direct Customer above
31 | Suppliers | Expect to be paid promptly | Risk | Purchasing | No | Manage company finances and A/P appropriately | Financials (confidential)
32 | Suppliers | Require access to quality and service requirements | Risk | Purchasing | Yes | Risk Register / Supplier Matrix | See Risk Register
33 | Suppliers | Vendor performance impacts on our delivery/quality | Mixed | Purchasing | Yes | Risk Register/Opportunity Register | See Risk Register Flowdown of reqs through Purchasing; probation/auditing if needed; management review records
34 | Competitors | Actively working to win business instead of, or away from, ACI | Risk | Sales/PM/Mkting | No | No Action: Accept Risk per Mgmt Decision | We win and retain customers based on our performance in all areas of the business; ACI is always striving for excellence.
35 | Legal | Concerned with company's exposure to litigation | Risk | All Processes/Depts | No | Management discussions with attorney | Legal records (confidential)
36 | Government & Regulatory Bodies | ACI must comply with all regulations and statutes | Risk | Legal | Yes | Risk Register | See Risk Register / Do this as normal part of business
37 | Government & Regulatory Bodies | Unclear roles and responsibilities between different business partners in the export process; lack of compliance safeguards throughout the entire export process. | Risk | Legal | No | No Action: Accept Risk per Mgmt Decision | Very Low Risk: Very few exports; customer defines the requirements
38 | Government & Regulatory Bodies | Must control location and access to Defense Articles and Technical Data | Risk | All Processes/Depts | Yes | Risk Register/FEMAs | See Risk Register
39 | Certification Body | Level of compliance to ISO 9001:2015 | Risk | All Processes/Depts | Yes | Risk Register / Internal Auditing | See Risk Register / Audit records
40 | Industry Associations | ACI seeks to adhere to these standards (IPC, NIST, etc.) | Risk | Production | Yes | No Action: largely satisfied for now | Adherence is standard Process / No special actions required
41 | Local Community | Wants our company to hire and retain local workers | Mixed | HR | No | No Action: largely satisfied for now | We do this naturally
42 | Local Community | Have concerns over waste and water management and other local regulations including property management and nearby land | Risk | Legal | Yes | See entry for Regulatory bodies | See Risk Register / Do this as normal part of business / Legal records (confidential)
43 | Local Community | Can provide positive press | Opportunity | Sales | No | No action, proceed normally for now | Maintain good relations locally
44 | All Stakeholders | Covid 19 Risks and Opportunities | Mixed | All Processes/Depts | Yes | Risk Register/Opportunity Register | Covid 19 has and will significantly impact the business in the near and mid terms. ACI will take immediate action to address the issues. See Risk and Opps for all information
45 | Customers (current or potential) | Major Logistics issues with entire supply chain | Mixed | Purchasing | Yes | Risk Register/Opportunity Register | The worldwide supply chain problem are causing major issues with sourcing parts

## Risk Register
COTO Log: Risk Register Rev. A
Unique ID | Process / Dept | Issue |  | Probability (of risk occurring) |  | Prob. Rating | Consequence (if risk is encountered) | [5 empty] | Cons. Rating | Risk Factor (Prob x Cons) | Mitigation Plan | Risk Factor after Mitigation
|  |  | Risk | Likelihood | Previous Occurrences |  | Potential Loss of Customer or Entire Contract | Potential Inability to Meet Immediate Job Requirements | Potential Risk to Human Health | Potential Violation of Regulations | Impact on Company Reputation | Est. Cost of Correction / Financial Penalty |  |  | (Required for risk factors >=10, suggested for risk factors between 5 and 10)
1 | All Processes/Depts | QMS processes must be efficient and effective | QMS processes may not be adequately efficient or effective to meet the business needs | Somewhat likely to occur | Has never occurred. | 2 | High | Very High | Minor | Possible | Severe | > $100,000 | 3.5 | 7 | ACI recognizes its QMS system has a large impact on ACIs firm commitment to quality and customer service. Management continually keeps abreast of all issues related to the QMS and takes action accordingly; this is logged in the Management Review Meeting minutes, To-Do Lists, FMEAs, CAPAs, etc. We have also hired a very qualified Quality Manager, who is helping management perform their required quality management tasks. | 2
2 | All Processes/Depts | Company must maintain Organizational Knowledge | Unmaintained organizational knowledge is lost, inaccessible, or out of date leading to ACIs inability to meet demands of customers and other parties | Somewhat likely to occur | Has occurred in past 5 years. | 3.5 | Moderate | Moderate | Minor | Possible | Moderate | > $100,000 | 2.8333 | 9.9167 | Management routinely discusses and addresses organizational knowledge to see if any major gaps in the knowledge base exist. Previously, this had been done "off-line" and unofficially as part of Management Review, but is now officially covered in the Management Review. Furthermore, top management is insisting on documentation follow-through and cross-training. See also: Training. | 3
5 | All Processes/Depts | Loss of our core differentiators and uniqueness | Harms our ability to progress towards our mission/vision | Somewhat likely to occur | Has never occurred. | 2 | Very High | Moderate | None / NA | Possible | Severe | > $500,000 | 3.3333 | 6.6667 | Management keeps an eye on negative changes or loss in our strengths. After 2015 is implemented with full fleshed out COTO log and strategic direction, we will ensure employee actions build on our strengths by writing them down, disseminating it, and training new and existing employee. During time of growth and transition, this is risk is heightened and is ongoing to a degree. | 5
6 | Executive | Too much change, too quickly | Causes impactful disruptions to the business | Likely to occur | Has occurred in past 5 years. | 4 | Moderate | Very High | Minor | Possible | Moderate | > $100,000 | 3.1667 | 12.6667 | Limit disruption to operations, financials, people and quality by instituting change at a manageable pace. Top management is developing a project/prioritization plan that will flow down to the departments and will be collectively collaborated on. "To do list" meetings, new operational discussions, and strategic suggestions from others to the CEO are selectively chosen and purposefully run with staggered and somewhat flexible deadlines. | 4
8 | Admin | Company must maintain sufficient and capable staff | Sufficient or capable staff is not provided to the departments to ensure an effective system to meet our goals and direction; loss of ACI time/money | Somewhat likely to occur | Has occurred in past year. | 4 | High | Very High | None / NA | Possible | Moderate | > $100,000 | 3.1667 | 12.6667 | Management routinely looks at staffing to ensure we are adequately staffed to the meet needs of our customers and the QMS; this is captured in the Management Review. Management vets all new hires rigorously. Tests and interviews are done until Management is satisfied with the candidate's viability. Candidates may be put on a temp to hire basis to ensure the candidate will be a successful employee of ACI. While the capability of staff hired is very good, during a phase of growth and transitions the sufficient headcount of the right staff to ensure a smooth growth or transition is a delicate balance and an ongoing risk. | 7
10 | HR/Training | Employees require appropriate training | Employees do not grow, perform their tasks effectively, or perform their tasks at all, resulting in low morale and engagement as well increased defects and lower quality. | Unlikely to occur | Has occurred in past 5 years. | 3 | Moderate | High | Moderate | Definite | Severe | > $100,000 | 3.5 | 10.5 | All employees are adequately trained per the qualifications document. Employee competence and training is covered in the Management Review meetings. Open and trustful feedback is being encouraged by top management. | 4
12 | Engineering | Employees require correct information and tools to do their job | Employees do not perform their tasks effectively, or cannot perform their tasks at all | Somewhat likely to occur | Has occurred in past 5 years. | 3.5 | High | Very High | Moderate | Definite | Severe | > $100,000 | 3.8333 | 13.4167 | Management and Engineering review the requirements of what is to be produced at ACI and ensure adequate tools/information are available for production and inspection. Employees are routinely encouraged to notify Engineering or Management if new/more tooling is needed. Product engineering & engineering services staff have been hired to provide additional control. | 3
13 | IT | Must create a comprehensive and effective system of IT/telecom resources and services | Data, equipment, or services are insufficient to allow departments to perform their functions | Somewhat likely to occur | Has never occurred. | 2 | High | Very High | None / NA | Possible | Severe | > $100,000 | 3.3333 | 6.6667 | IT data, equipment and services are used and reviewed by staff during the course of the day; missing data, inadequate services, or any issues are immediately notified to IT, and is corrected promptly (IT is always on call). IT reinforcements are also on dial to assist where necessary. IT also has a project plan in place (confidential). | 4
14 | IT | Provides redundancy and backup plans | User error, acts of God or security penetrations cause disruption or loss of or access to data | Somewhat likely to occur | Has not occurred in past 10 years. | 2.5 | Very High | Very High | High | Definite | Very severe | > $500,000 | 4.5 | 11.25 | All data on the ACI servers is backed up daily so that no information is lost. | 3
16 | Production | Requires adequate equipment and facilities and safe working conditions | Facilities / equipment is inadequate, derelict, or creates a poor work environment thereby creating defects and/or not meeting needs of production, QMS, and customers. | Somewhat likely to occur | Has occurred in past 10 years. | 3 | High | Moderate | Moderate | Possible | Moderate | > $100,000 | 3.1667 | 9.5 | Maintenance is routinely performed on all machines required for production as needed; Maintenance, equipment, and facility adequacy is reviewed during the Management Review Meeting. Our facilities, tech and equipment is able to meet the demands of the market/clients. | 4
17 | Production | Customer expects high quality products | Products are built poorly; customer returns units or is otherwise unsatisfied. We or the customer lose business, time, money, customer satisfaction. | Unlikely to occur | Has occurred in past year. | 3.5 | Minor | Moderate | None / NA | Possible | Moderate | < $100,000 | 2.3333 | 8.1667 | Multiple mitigation factors. See both the Engineering Services and Material/Production/Shipping FMEAs for full details. Efficacy and implementation are addressed during Management Review. Customer feed back log and metrics are recorded and reviewed on a frequent basis. ACI has a history of delighting the customer and meeting our deliverables. | 3
18 | Packing/Shipping | Customer expect on time delivery | Loss of customer satisfaction; ACI or customer lose business because of late delivery | Unlikely to occur | Has occurred in past 10 years. | 2.5 | Moderate | High | None / NA | None / NA | Severe | < $100,000 | 2.6667 | 6.6667 | Multiple mitigation factors. See both the Engineering Services and Material/Production/Shipping FMEAs for full details. Efficacy and implementation are addressed during Management Review. Customer feed back log and metrics are recorded and reviewed on a frequent basis. ACI has a history of delighting the customer and meeting our deliverables. | 3
20 | Sales/PM/Marketing | Customer expects good customer service | ACI does not provide the level of customer service it's customers require | Unlikely to occur | Has occurred in past 10 years. | 2.5 | High | High | None / NA | None / NA | Severe | > $100,000 | 3 | 7.5 | ACI regularly reviews customer feedback via discussions across staff and which is tracked in the feedback log. Customer feedback is also reviewed during the management review meetings. ACI consistently delights it's customers. | 2
21 | All Processes/Depts | Customer Flows down their QMS requirements | Customer does not adequately communicate their quality requirements | Likely to occur | Has occurred in past year. | 4.5 | Minor | Very High | Minor | Definite | Moderate | > $100,000 | 3.1667 | 14.25 | ACI reviews all PO and build data beforehand; in cases where we feel information is missing we will ask the customer for supplier and quality requirements before building product. ECO and deviation protocols ensure all customer requirements are met. | 4
32 | Purchasing | Vendor requires access to quality and service requirements | Vendor may not know what is expected of them; wrong service or product supplied | Unlikely to occur | Has occurred in past 10 years. | 2.5 | Minor | Moderate | None / NA | None / NA | Minimal | < $10,000 | 1.8333 | 4.5833 | ACI provides all detail necessary for suppliers to meet our requirements; ACI's quality policy is available on the internet for review. All suppliers are monitored using our Supplier Matrix Table | 2
33 | Purchasing | Vendor performance impacts on our delivery/quality | Vendor does not ship the right components and or quantity; vendor does not ship components in a timely fashion. Effects ACI's customer service and objectives | Somewhat likely to occur | Has occurred in past 5 years. | 3.5 | Minor | Moderate | None / NA | None / NA | Minimal | < $10,000 | 1.8333 | 6.4167 | ACI provides all detail necessary for suppliers to meet our requirements; ACI's quality policy is available on the internet for review. All suppliers are monitored using our Supplier Matrix Table | 3
36 | Legal | ACI Must comply with all regulations and statutes | ACI can be fined or otherwise penalized; possible harmful effects on the environment. | Unlikely to occur | Has never occurred. | 1.5 | High | High | High | Legal Risk | Severe | > $500,000 | 4.3333 | 6.5 | All regulatory requirements are complied with as a natural part of our business. Management is aware of all the regulations we are required to comply with, and meet or exceed all expectations from both a legal standpoint, and the health of the environment/community. Attorneys also provide counsel, assure compliance to local laws. As far as can be determined, there have been no lapses in compliance with any regulations in the history of the company. | 2
38 | All Processes/Depts | Must control location and access to Defense Articles and Technical Data | Potentially sensitive information is supplied to the wrong parties | Unlikely to occur | Has never occurred. | 1.5 | High | High | None / NA | Legal Risk | Severe | > $100,000 | 3.6667 | 5.5 | All ITAR data is kept in limited access files on a server with no outside internet access and hard copy files in a secure room. All ITAR data is sent via encrypted zip files or secure FTP servers with passwords sent using a different email address, or over the phone to keep them separate. All product is manufactured in a secure environment. Customers are notified if ACI feels that they do not use sufficient means for securing the data. | 2
39 | Quality | Level of compliance to ISO 9001:2015 | Staff is not trained to the QMS and cannot meet ISO requirements; Management is not trained in the specifics of the QMS or ISO 9001:2015 | Unlikely to occur | Has occurred in past 10 years. | 2.5 | Moderate | High | None / NA | None / NA | Moderate | < $100,000 | 2.5 | 6.25 | Training has been provided to both the general employees and Management to ensure compliance with the standard; Top Management undergone 2015 awareness training to make them familiar with the changes to the standard from 2008 to 2015. A gap analysis was completed and a reassessment and audit to the new standard was done no glaring issues with the QMS were discovered. | 3
44 | All Processes/Depts | Covid 19 Pandemic | The spread of the Coronavirus-19 can impact the entire supply chain, including daily operations at ACI. This could include, but is not limited to. Late supply and material deliveries. Worker health and safety, Customer health and safety, Possible plant shutdown (in event of outbreak at ACI), PO cancellation, order delivery problems. Customers closing shop. work efficiency, workers quitting, company perception, loss of business, etc. | Likely to occur | Has occurred in past year. | 5 | High | High | High | None / NA | Severe | > $500,000 | 5 | 25 | Steps ACI is taking to mitigate risks. -Having people work from home as much as possible. -Workers will be split into teams to reduce risk of contact infection. -Surfaces will be sterilized in frequent intervals throughout the day. -Workers will also be split between building to reduce infection risks. -Masks and gloves will be given to employees (depending on contact and interaction risks) and social distancing will be implemented to reduce contact. -Handwashing buddy system and cleaning schedules will be implemented. -High risk employees will be segregated from general population as much as possible. -Incoming material and Work in progress will be sanitized and/or handled appropriately to help ensure worker and customer safety. -Covid 19 action letters have been sent to active customers and also posted on the website -ACI will immediately inform the customers of any adjustments made to the delivery schedule. ACI will do its utmost to set, achieve and maintain reasonable OTD or all customers. -After implementing all of the controls shown above ACI has sucefully mitiagated the Covid-19 risk to lower levels than previously thought. No outbreak of the virus has occured during the pandemic at American Circuits | 3
45 | Purchasing | Major Logistics issues with entire supply chain | The worldwide supply chain problem are causing major issues with sourcing parts. Purchasing may not be able to get parts in time for the Customer's requirements, or possibly not at all. Part prices can continue to rise, making it difficult to competitively quote or purchase components. | Very likely to occur | Has never occurred. | 4 | High | Very High | None / NA | None / NA | Severe | > $500,000 | 4 | 16 | Steps ACI is taking to mitigate risks. - Immediately identifiing High risk parts and putting those at the top of the list for purchase. - Work with the customer to see if they have the ability to send the parts or source it through there channels. Have them consign the parts to us, if necessary. - When buying scare/highdollar components, purchase more then needed if a forcast for use is available from the customer. - Keep in constant contact with out distributors to make sure they keep us in the loop concernign part availability. Work with internal and customer engineers to find ssuitable subs or alternates. | 4
Note on E3: This is an estimate of how likely you think the risk is; what is the chance of it happening.
Note on F3: This is a consideration of whether the risk has already happened; an unlikely risk may still have happened recently, so this helps dial in the Probability number a bit.
Note on H3: Here the risk is so bad, the customer pulls ALL their orders or work from your company.
Note on I3: This column reflects the risk impacting on only the immediate job you're working on; not the entire customer contract. This might be for a single order or single delivery.
Note on J3: This is dependent on the risk: might be harm or injury to your workers in some cases, might be harm to the customer or public in other cases. It depends on each risk.
Note on K3: This means the risk would cause you to violate some law, statute, regulation, etc.
Note on L3: This is the potential damage on your "brand" or reputation in the industry, if the risk happens
Note on M3: This is your estimate of how much $$ this risk will cost you, either to repair something when the risk occurs, or due to some other potential penalty. Higher costs are worse.

## Opp Register
|  | COTO Log: Opportunity Register Rev. A | [11 empty] | Number of active improvement activities: | 11
Unique ID | Process / Dept | Opportunity | Probability (of achieving opportunity) |  | Prob. Rating | Benefit (if opportunity is encountered) | [5 empty] | Ben. Rating | Opp Factor (Prob x Ben) | Opportunity Pursuit Plan (suggested for Opp Factors >=10) May reference external planning document | Post- Implementation Success? | Status | If Failed, Why?
|  |  | Likelihood | Previous Occurrences |  | Potential for New Business | Potential Expansion of Current Business | Potential improvement in satisfying regulatory requirements | Potential improvement to internal QMS processes | Improvement to Company Reputation/Brand | Potential Cost of Implementation
1 | Quality | Maintaining a top-notch QMS will be ACI more attractive to potential clients/customers. Less repair/rework will help the bottom-line. | Very likely to occur | Has occurred in past year. | 5 | High | High | Minor | Very High | Good impact | < $100,000 | 3.6667 | 18.3333 | Continue to work on improving the QMS and using it as a tool to improve our processes, delivery, and quality of products and services. Continue to strengthen the Quality department. | On-Going Project | OPEN
10 | All Processes/Depts | A better trained staff and a great culture is a core differentiator vs other competitors. While qualitative in nature, it impacts every aspect of our business and is a key driver in achieving our mission/vision | Likely to occur | Has occurred in past year. | 4.5 | High | Very High | High | Very High | Great impact | > $100,000 | 4.1667 | 18.75 | -- Invest in staff development vis training, coaching, improved on boarding, defining roles, promoting feedback and clarifying expectations. -- Improve culture and harmony by championing teamwork, communication, professionalism, trust and integrity. -- Create a mindset of persistent improvement by instilling responsibility, providing employees a safe voice, making feedback routine, and reinforcing positive and selfless behavior. | On-Going Project | OPEN
22 | Sales/PM/Mkting | Growing the company will have significant financial benefits to ACI. | Likely to occur | Has occurred in past year. | 4.5 | Very High | High | Minor | Minor | Great impact | > $100,000 | 3.3333 | 15 | Sales department creation and addition of new salespeople; website and marketing improvements; improved quotation model; adequate staffing to support growth; see strategic direction. Managements actions to help grow the company will allow ACI to be better positioned in the marketplace and move further along it's vision/mission. Note: mgmt seeks to grow via volume vs pricing, thereby not sacrificing existing customers | On-Going Project | OPEN
23 | Sales/PM/Mkting | Expanding business with current happy customers. | Likely to occur | Has occurred in past year. | 4.5 | Moderate | High | None / NA | Minor | Good impact | < $10,000 | 3 | 13.5 | Keeping engaged with the customers to make sure they're delighted with us will help ACI win new business from different departments and people within the company | On-Going Project | OPEN
24 | All Processes/Depts | Consolidation of most assembly operations and facilities renovations to improve efficiencies, process flow, operations control, working environment, and customer impressions | Very likely to occur | Has not occurred in past 10 years. | 3.5 | High | High | Minor | Moderate | Good impact | > $500,000 | 3 | 10.5 | Identify operational and real estate needs and develop master project plan | On-Going Project | OPEN
25 | Engineering | Better functional SMT operations which is central to growth | Likely to occur | Has occurred in past 5 years. | 4 | Moderate | High | None / NA | Moderate | Moderate impact | > $100,000 | 2.6667 | 10.6667 | Improve SMT operations including programming, productivity, attrition and analytics with a mind for quality. Engineering team will lead the way, serving as central point of coordination between top management and production. | On-Going Project | OPEN
26 | Production | More efficient labor utilization and feedback into our quote system will improve our operations as well as our financial health | Likely to occur | Has occurred in past 5 years. | 4 | High | Moderate | None / NA | Minor | Moderate impact | < $10,000 | 2.8333 | 11.3333 | Implement review of labor yield/efficiency and bolster reporting back to Sales and Management . This information will feed into our quotation model, enhancing our estimation capabilities/accuracy, as well as be discussed by management to improve our future production times. | On-Going Project | OPEN
27 | Receiving/Inventory | New inventory system to transition from kits to centralized inventory will enhance controls, boost customer confidence, improve purchasing, and save space. | Very likely to occur | Has occurred in past year. | 5 | Moderate | Moderate | Minor | High | Good impact | < $100,000 | 3.1667 | 15.8333 | Continue implementation of inventory system and the loading of parts, after which controls are in place to track issues by work order, ESD/MSD control, inventory reporting. | Met all expectations | CLOSED
28 | Sales/PM/Mkting | Good relationships with all stakeholders (suppliers, customers, etc) could result in referrals to new clients/customers. | Somewhat likely to occur | Has occurred in past year. | 4 | High | Minor | None / NA | Minor | Moderate impact | < $10,000 | 2.6667 | 10.6667 | Keeping engaged with stakeholders to make sure they're delighted with us will help ACI win new business. Asking customers if they or anyone they know has a need for our services is made apparent within their circle of influence | On-Going Project | OPEN
33 | Purchasing | Maintaining a great supply chain makes us more nimble and efficient and allows us to pass savings in time and money on to our customers. | Likely to occur | Has occurred in past year. | 4.5 | Moderate | Moderate | None / NA | High | Good impact | < $100,000 | 3 | 13.5 | Extend our local and international supply chain to support our customers’ engineering, assembly, board, and cable needs. Persistently improve the vendor base’s quotations, costs, terms, lead times, on-time deliveries, quality and risk. | On-Going Project | OPEN
44 | All Processes/Depts | Covid 19 Pandemic may allow us to receive business from competitors who are unable to meet the demands of their customers during the pandemic | Likely to occur | Has occurred in past year. | 4.5 | High | High | None / NA | None / NA | Great impact | < $100,000 | 3 | 13.5 | Send out notes to existing customers to let them no that ACI is an essential business and that we will not be closing during the pandemic crisis unless absolutely necessary. Put letter of Covid 19 action on website to let potential customers know that ACU is open. Have office personnel available during business hours to take order and answer questions even if all staff if working from home. | On-Going Project | OPEN
45 | Engineering | Current Logistics issues may allow us to assist with redesign. | Likely to occur | Has occurred in past year. | 4.5 | High | Moderate | None / NA | None / NA | Great impact | < $100,000 | 2.8333 | 12.75 | If problems with part sorcing are becoming too big to surmount. Remind customers about our Engineering Services and see if they a open to letting us assist in redesign th e boards around readily available componenents, if possible. | On-Going Project | OPEN
Many opportunities exist; we are using the opportunity register to catalog and identify opportunities that significantly impact the QMS and are deemed immediately actionable.
Note on P2: Max Johnson: Most projects will stay On-Going unless there is no more work to be done. In most instances there is always more improvements to be made.
Note on D3: What is the likelihood that you can obtain this opportunity?
Note on E3: Have you obtained this opportunity previously?
Note on G3: Could the opportunity result in you getting new customers or breaking into new markets?
Note on H3: Could the opportunity result in your current customers increasing their business with you?
Note on I3: Could this opportunity help you meet laws, statutes, regulations, etc?
Note on J3: Will these changes make a significant positive impact on the QMS system?
Note on K3: What's the potential for this opportunity to improve your reputation in the industry or your brand?
Note on L3: How much will this cost to implement? Lower costs are better, in this case.

## Lists
OPP RATING LIMIT: | RISK RATING LIMIT: | Type | Priority | Treatment | Bias | Process/Dept | Likelihood | Occurrences | Potential | Violation | correction | reputation | cost of opp | reputation | score | Success | Yes/No
10 | 10 | External | Emergency | No Action: Accept Risk per Mgmt Decision | Opportunity | All Processes/Depts | Cannot occur / not applicable | Has never occurred. | None / NA | None / NA | $ 0 | None | > $500,000 | No impact / NA | 1 | Opportunity Failed | Yes
| RISK CONSIDERATION LIMIT | Internal | High | Risk Register / FMEA Style | Risk | Sales/PM/Mkting | Unlikely to occur | Has not occurred in past 10 years. | Minor | Possible | < $10,000 | Minimal | > $100,000 | Minimal impact | 2 | Opportunity Abandoned | No
| 5 |  | Medium | Root Cause Analysis | Neutral | Engineering | Somewhat likely to occur | Has occurred in past 10 years. | Moderate | Definite | < $100,000 | Moderate | < $100,000 | Moderate impact | 3 | Met some expectations
|  |  | Low | Internal Auditing | Mixed | Purchasing | Likely to occur | Has occurred in past 5 years. | High | High | > $100,000 | Severe | < $10,000 | Good impact | 4 | Met all expectations
|  |  |  | Root Cause Analysis |  | Receiving/Inventory | Very likely to occur | Has occurred in past year. | Very High | Legal Risk | > $500,000 | Very severe | $0 or N/A | Great impact | 5 | Exceeded expectations
|  |  |  | Corrective Action Request (CAR) |  | Production | [9 empty] | On-Going Project
|  |  |  | Vendor Auditing |  | Packing/Shipping
Opportunity Trend Data |  |  |  | Other Auditing |  | HR/Training
Number Open Improvement Initiatives | 9 |  |  | Management Review Activity |  | IT
Number Closed Improvement Initiatives | 1 |  |  | Marketing Enhancement |  | Finance/Accounting
Total Improvement Initiatives to Date | 11 |  |  | Other |  | Legal
Opportunity Failed | 0 |  |  | Opportunity Register |  | Quality
Opportunity Abandoned | 0 |  |  |  |  | Admin
Met some expectations | 0 |  |  |  |  | Top Management | [11 empty] | (Required for risk factors >=
Met all expectations | 1 | [16 empty] | , suggested for risk factors between
Exceeded expectations | 0
(Required for risk factors >=10, suggested for risk factors between 5 and 10)
Risk Trend Data
Total risks processed | 21 | [16 empty] | Opportunity Pursuit Plan (suggested for Opp Factors >=
Total risks requiring action | 8 | [16 empty] | ) May reference external planning document
Total risks suggesting action | 12
Total risks accepted without action | 1 | [16 empty] | Opportunity Pursuit Plan (suggested for Opp Factors >=10) May reference external planning document
The Risk Rating Limit is the minimum risk score which will trigger a MANDATORY mitigation plan.
The Risk Consideration Limit is a score which would trigger a SUGGESTED mitigation plan.
The Opportunity Rating Limit is the minimum score which would require a mandatory "opportunity pursuit plan."

## Rev Rec
REVISION RECORD
Sheet(s) Affected | Section/Item Affected | Changes | Rev | Changed By | Change Date
All | All | Initial Release | A | MJ | 2018-03-10
Issues / Risk / Opp | Minor / Various | Ket: Original capture of Risk/Opps was superb and requires only minor updates. Closed Inv System Opp (item 27) | B | KG | 2019-01-06
All | All | Ket: COTO log needed updates to reflect ACI's COVID 19 response. Max Johnhson will update and create PAR. | C | KG | 2020-02-25
Risk | 44 | Max: Updated log to document effectivness of Covid actions. Created and closed PAR (1050 | D | MJ | 2021-03-05
Note: Minor changes to wording to not need to be rev controlled. If you change perinate information for the Parties, Factors, Risks or Opportunities, save the old version with the date at the end of the file name and archive. Changes to the actual Risk Register (i.e. columns, risk action levels, etc.) will be captured on this page.